## Sheet1
Employee Name |  | 2026-06-01 | 2026-06-02 | 2026-06-03 | 2026-06-04 | 2026-06-05 | 2026-06-06 | 2026-06-07 | 2026-06-08 | 2026-06-09 | 2026-06-10 | 2026-06-11 | 2026-06-12 | 2026-06-13 | 2026-06-14 | 2026-06-15 | 2026-06-16 | 2026-06-17 | 2026-06-18 | 2026-06-19 | 2026-06-20 | 2026-06-21 | 2026-06-22 | 2026-06-23 | 2026-06-24 | 2026-06-25 | 2026-06-26 | 2026-06-27 | 2026-06-28 | 2026-06-29 | 2026-06-30
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday
SasiKumar Goonasegaran | Job Name | Public Holiday | E09/E10 RRU Termination + CT Installation - NS (PO2 - Rob Cook) Pre-start at 10.30pm - Mon Night | E09/E10 RRU Termination + CT Installation - NS (PO2 - Rob Cook) | E09/E10 RRU Termination + CT Installation - NS (PO2 - Rob Cook) | J33 PIM NS |  |  | J41/J42 CW Supervision | R32/R33 Prep Works | R32/R33 NS (10 Hrs Ext.) + Cat 5 (NS) | R32/R33 NS (10 Hrs Ext.) + Cat 5 (NS) | R32/R33 Rest Day |  |  | T08/T09 WODZ Works | T08/T09 WODZ Works | T08/T09 WODZ Works | T08/T09 WODZ Works | T08/T09 WODZ Works |  |  | J54 Tunnel (NS) PUG Tunnel 5 | J54 Tunnel (NS) PUG Tunnel 5 | J54 Tunnel (NS) PUG Tunnel 5 | J54 Tunnel (NS) PUG Tunnel 5 | J54 Tunnel (NS) PUG Tunnel 5 |  | J41/J42 10PM | J41/J42 | J41/J42
Michael Petronio | Job Name | Public Holiday | E09/E10 RRU Termination + CT Installation - NS (PO2 - Rob Cook) Pre-start at 10.30pm - Mon Night | E09/E10 RRU Termination + CT Installation - NS (PO2 - Rob Cook) | E09/E10 RRU Termination + CT Installation - NS (PO2 - Rob Cook) | E09/E10 - DS |  | M19 (Quote on M20) (08AM) | M19 (Quote on F19) (08AM) | R32/R33 Prep Works | R32/R33 NS (10 Hrs Ext.) + Cat 5 (NS) | R32/R33 NS (10 Hrs Ext.) + Cat 5 (NS) | R32/R33 Rest Day |  |  | T08/T09 WODZ Works | T08/T09 WODZ Works | T08/T09 WODZ Works | T08/T09 WODZ Works | T08/T09 WODZ Works |  |  | J54 Tunnel (NS) PUG Tunnel 5 | J54 Tunnel (NS) PUG Tunnel 5 | J54 Tunnel (NS) PUG Tunnel 5 | J54 Tunnel (NS) PUG Tunnel 5 | J54 Tunnel (NS) PUG Tunnel 5 |  | J41/J42 10PM | J41/J42 | J41/J42
Mudassar Ayaz | Job Name | Public Holiday | E09/E10 RRU Termination + CT Installation - NS (PO2 - Rob Cook) Pre-start at 10.30pm - Mon Night | E09/E10 RRU Termination + CT Installation - NS (PO2 - Rob Cook) | E09/E10 RRU Termination + CT Installation - NS (PO2 - Rob Cook) | EL |  |  | SB | R32/R33 Prep Works | R32/R33 NS (10 Hrs Ext.) + Cat 5 (NS) | R32/R33 NS (10 Hrs Ext.) + Cat 5 (NS) | Tx (Site IDs TBC) |  |  | R44 IBC | R44 IBC | R44 IBC | R44 IBC | R44 IBC |  |  | R44 IBC | R44 IBC | R44 IBC | R44 IBC | R44 IBC |  |  | SB | SB
Naveen Suragani | Job Name | Public Holiday | E09/E10 OEC + IER finalisation + Testing + Software + SCF loading + RRU Power up P2E: 135349 | E09/E10 OEC + IER finalisation + Testing + Software + SCF loading + RRU Power up P2E: 135349 | E09/E10 OEC + IER finalisation + Testing + Software + SCF loading + RRU Power up P2E: 135349 | E09/E10 - DS |  | M19 (Quote on M20) (08AM) | M19 (Quote on F19) (08AM) | SB | SB | Tx | Tx (Site IDs TBC) + Sparky |  |  | T08/T09 WODZ Works | T08/T09 WODZ Works | T08/T09 WODZ Works | T08/T09 WODZ Works | T08/T09 WODZ Works |  |  | J54 Tunnel (NS) PUG Tunnel 5 | J54 Tunnel (NS) PUG Tunnel 5 | J54 Tunnel (NS) PUG Tunnel 5 | J54 Tunnel (NS) PUG Tunnel 5 | J54 Tunnel (NS) PUG Tunnel 5 |  | J41/J42 10PM | J41/J42 | J41/J42
Barita Sitompul | Job Name | Public Holiday | E09/E10 OEC + IER finalisation + Testing + Software + SCF loading + RRU Power up P2E: 135349 | E09/E10 OEC + IER finalisation + Testing + Software + SCF loading + RRU Power up P2E: 135349 | E09/E10 OEC + IER finalisation + Testing + Software + SCF loading + RRU Power up P2E: 135349 | TBC |  |  | R01 OEC Works | R01 OEC Works | R01 OEC Works | R01 OEC Works | R01 OEC Works |  |  | E18 Morley Station Revisit | E18 Morley Station Revisit | E18 Morley Station Revisit | E18 Morley Station Revisit | E18 Morley Station Revisit |  |  | J36 Revisit (NS) (PO3) | J36 Revisit (NS) (PO3) | J36 Revisit (NS) (PO3) | J36 Revisit (NS) (PO3) | J36 Revisit (NS) |  |  | SB | SB
Aqeel Hussain | Job Name | Public Holiday | E11/E12 + OEC + DS PO1 Nokia (Jason Owen (0430 620 448) eTAS: 03-551-26 P2E: 135360 | E11/E12 + OEC + DS PO1 Nokia (Jason Owen (0430 620 448) eTAS: 03-551-26 P2E: 135360 | E11/E12 + OEC + DS PO1 Nokia (Jason Owen (0430 620 448) eTAS: 03-551-26 P2E: 135360 | E11/E12 + OEC + DS PO1 Nokia (Jason Owen (0430 620 448) eTAS: 03-551-26 P2E: 135360 |  |  | R32/R33 SPD + Comms Room Works | R32/R33 SPD + Comms Room Works | R32/R33 SPD + Comms Room Works | R32/R33 SPD + Comms Room Works | R32/R33 SPD + Comms Room Works |  |  | SB | SB | SB | SB | SB |  |  | F12 + Cat 5 (Ext NS) | F12 + Cat 5 (Ext NS) | F12 + Cat 5 (Ext NS) | F12 + Cat 5 (Ext NS) | F12 + Cat 5 (Ext NS) |  |  | SB | SB
Sreerag Varikkottil | Job Name | Public Holiday | E11/E12 Cage + RRU + CT installation + DS eTAS: 03-551-26 P2E: 135360 | E11/E12 Cage + RRU + CT installation + DS eTAS: 03-551-26 P2E: 135360 | E11/E12 Cage + RRU + CT installation + DS eTAS: 03-551-26 P2E: 135360 | E11/E12 RRU + Termination + IER/OEC + DS PO1 Nokia (Jason Owen (0430 620 448) |  |  | R32/R33 SPD + Comms Room Works | R32/R33 SPD + Comms Room Works | R32/R33 SPD + Comms Room Works | R32/R33 SPD + Comms Room Works | R32/R33 SPD + Comms Room Works |  |  | SB | SB | SB | SB | SB |  |  | F11/F12 + Cat 5 (Ext NS) | F11/F12 + Cat 5 (Ext NS) Freo Tunnel 6 | F11/F12 + Cat 5 (Ext NS) Freo Tunnel 6 | F11/F12 + Cat 5 (Ext NS) Freo Tunnel 6 | F11/F12 + Cat 5 (Ext NS) Freo Tunnel 6 |  | J41/J42 10PM | J41/J42 | J41/J42
Chima | Job Name | Public Holiday | E11/E12 Cage + RRU + CT installation + DS eTAS: 03-551-26 P2E: 135360 | E11/E12 Cage + RRU + CT installation + DS eTAS: 03-551-26 P2E: 135360 | E11/E12 Cage + RRU + CT installation + DS eTAS: 03-551-26 P2E: 135360 | E11/E12 RRU + Termination + IER/OEC + DS PO1 Nokia (Jason Owen (0430 620 448) |  |  | R44 IBC | R44 IBC | R44 IBC | R44 IBC | R44 IBC |  |  | R44 IBC | R44 IBC | R44 IBC | R44 IBC | R44 IBC |  |  | R21 Revisit | R21 Revisit | R21 Revisit | SB | SB |  |  | SB | SB
Biren | Job Name | Public Holiday | E11/E12 IER + Software + SCF loading + All testing + DS eTAS: 03-551-26 P2E: 135360 | E11/E12 IER + Software + SCF loading + All testing + DS eTAS: 03-551-26 P2E: 135360 | TBC | E11/E12 IER + DS |  |  | J41/J42 OEC Works | J41/J42 OEC Works | J41/J42 OEC Works | J41/J42 OEC Works | J41/J42 OEC Works |  |  | SB | SB | SB | SB | J18 Revisit Fiber run, test and HOP |  |  | SB | SB | R19 IER Revisit (PO1) | R19 IER Revisit (PO1) | SB |  |  | SB | SB
Noman Aslam | Job Name | Public Holiday | SL | SL | M01 Macro (IER) + MO1E Cable + Cable tray installation P2E: 130877 | M01 Macro (IER) + MO1E Cable + Cable tray installation P2E: 130877 |  |  | R01 OEC Works | R01 OEC Works | R01 OEC Works | R01 OEC Works | R01 OEC Works |  |  | SB | SB | SB | SB | J18 Reviist Fiber run, test and HOP |  |  | SB | SB | R19 IER Recivit+PO | R19 IER Recivit+PO | SB |  |  | SB | SB
Garry | Job Name | Public Holiday | J15 Revisit (PO1 - Peter M) eTAS: 03-631-26 P2E: 132993 | M01 Macro (IER) + MO1E Cable + Cable tray installation P2E: 130877 | M01 Macro (IER) + MO1E Cable + Cable tray installation P2E: 130877 | M01 Macro (IER) + MO1E Cable + Cable tray installation P2E: 130877 |  |  | E15 IBC Revisit | E15 IBC Revisit | E15 IBC Revisit | SB | SB |  |  | SB | SB | SB | SB | SB |  |  | R44 IBC | R44 IBC | R44 IBC | R44 IBC | R44 IBC |  |  | R44 IBC | R44 IBC
Sebin Sebastian | Job Name | Public Holiday | R44 IBC - NS - PO1 Chris T P2E: 130854 ¦¦ eTAS: 03-713-26 Cage + RRU installation + Material delivery | R44 IBC - NS - PO1 Chris T P2E: 130854 ¦¦ eTAS: 03-713-26 Cage + RRU installation + Material delivery | R44 IBC - NS - PO1 Chris T P2E: 130854 ¦¦ eTAS: 03-713-26 | R44 IBC - NS - PO1 Chris T P2E: 130854 ¦¦ eTAS: 03-713-26 |  |  | R44 IBC | R44 IBC | R44 IBC | R44 IBC | R44 IBC |  |  | E18 Morley Station Revisit | E18 Morley Station Revisit | E18 Morley Station Revisit | E18 Morley Station Revisit | E18 Morley Station Revisit |  |  | J36 Revisit (NS) (PO3) | J36 Revisit (NS) (PO3) | J36 Revisit (NS) (PO3) | J36 Revisit (NS) (PO3) | J36 Revisit (NS) |  |  | R44 IBC | R44 IBC
Cosmas Dzvifu | Job Name | Public Holiday | R44 IBC - NS - PO1 Chris T P2E: 130854 ¦¦ eTAS: 03-713-26 Cage + RRU installation + Material delivery | R44 IBC - NS - PO1 Chris T P2E: 130854 ¦¦ eTAS: 03-713-26 Cage + RRU installation + Material delivery | R44 IBC - NS - PO1 Chris T P2E: 130854 ¦¦ eTAS: 03-713-26 | R44 IBC - NS - PO1 Chris T P2E: 130854 ¦¦ eTAS: 03-713-26 |  |  | R44 IBC | R44 IBC | R44 IBC | R44 IBC | R44 IBC |  |  | E18 Morley Station Revisit | E18 Morley Station Revisit | E18 Morley Station Revisit | E18 Morley Station Revisit | E18 Morley Station Revisit |  |  | J36 Revisit (NS) (PO3) | J36 Revisit (NS) (PO3) | J36 Revisit (NS) (PO3) | J36 Revisit (NS) (PO3) | J36 Revisit (NS) |  |  | SB | SB
Desire Chitsiga | Job Name | Public Holiday | R44 IBC - NS - PO1 Chris T P2E: 130854 ¦¦ eTAS: 03-713-26 Cage + RRU installation + Material delivery | R44 IBC - NS - PO1 Chris T P2E: 130854 ¦¦ eTAS: 03-713-26 | R44 IBC - NS - PO1 Chris T P2E: 130854 ¦¦ eTAS: 03-713-26 | R44 IBC - NS - PO1 Chris T P2E: 130854 ¦¦ eTAS: 03-713-26 |  |  | R44 IBC | R44 IBC | R44 IBC | R44 IBC | R44 IBC |  |  | R44 IBC | R44 IBC | R44 IBC | R44 IBC | R44 IBC |  |  | J36 Revisit (NS) (PO3) | J36 Revisit (NS) (PO3) | J36 Revisit (NS) (PO3) | J36 Revisit (NS) (PO3) | J36 Revisit (NS) |  |  | SB | SB
Panji | Job Name | Public Holiday | R44 IBC - NS - PO1 Chris T P2E: 130854 ¦¦ eTAS: 03-713-26 Cage + RRU installation + Material delivery | E09/E10 RRU Termination + CT Installation - NS (PO2 - Rob Cook) | R44 IBC - NS - PO1 Chris T P2E: 130854 ¦¦ eTAS: 03-713-26 | R44 IBC - NS - PO1 Chris T P2E: 130854 ¦¦ eTAS: 03-713-26 |  |  | E15 IBC Revisit | E15 IBC Revisit | E15 IBC Revisit | SB | SB |  |  | R44 IBC | R44 IBC | R44 IBC | R44 IBC | R44 IBC |  |  | SB | SB | SB | SB | SB |  |  | SB | SB
Reymar | Job Name | Public Holiday | E21 Revisit P2E:121246 | E21 Revisit P2E:121246 | E06 Revisit | E06 Revisit |  |  | E01 Revisit | E06 Revisit | E04 Revisit | J20 Revisit | E05 Revisit |  |  | E01 NOI | E06 NOI | E04 NOI | J20 NOI | E05 NOI |  |  | SB | SB | SB | SB | SB |  |  | SB | SB
Sea | Job Name | Public Holiday | E21 Revisit P2E:121246 | E21 Revisit P2E:121246 | E06 Revisit | E06 Revisit |  |  | E01 Revisit | E06 Revisit | E04 Revisit | J20 Revisit | E05 Revisit |  |  | E01 NOI | E04 NOI | E04 NOI | J20 NOI | E05 NOI |  |  | R44 IBC | R44 IBC | R44 IBC | R44 IBC | R44 IBC |  |  | R44 IBC | R44 IBC
Sudeep | Job Name | Public Holiday | T12 (NS) + Snags Clearance (PO1 - Joy Norris - 0419 039 809) eTAS: 01-719-26 P2E: 127240 | E13 (NS) + Snags Clearance (PO1 - Joy Norris - 0419 039 809) eTAS: 03-717-26 P2E: 124383 | F19 Revisit (DS) + AC Reworks + Cage + RRU installation P2E:143071 | F19 Revisit (DS) P2E:143071 |  |  | E15 IBC Revisit | E15 IBC Revisit | E15 IBC Revisit | SB | SB |  |  | J10 Macro + TMP +DP | J10 Macro + TMP +DP | J10 Macro + TMP +DP | J10 Macro + TMP +DP | J05 OEC + TMP +DP |  |  | J05 OEC + TMP +DP | J05 OEC + TMP +DP | R25 IER +PO1 | R25 IER +PO1 | R25 IER +PO1 |  |  | F03 Revisit +PO1 | F03 Revisit +PO1
JZ | Job Name | Public Holiday | T12 (NS) + Snags Clearance (PO1 - Joy Norris - 0419 039 809) eTAS: 01-719-26 P2E: 127240 | E13 (NS) + Snags Clearance eTAS: 03-717-26 P2E: 124383 | F19 Revisit (DS) + AC Reworks + Cage + RRU installation P2E:143071 | F19 Revisit (DS) P2E:143071 |  |  | SB | SB | SB | J41/J42 RRU + Cage Installation | J41/J42 RRU + Cage Installation |  |  | SB | SB | SB | SB | SB |  |  | R44 IBC | R44 IBC | R44 IBC | R44 IBC | R44 IBC |  |  | SB | SB
Kaka | Job Name | Public Holiday | R21 Revisit MOA (PO1 - James Macneall - 0427 816 906 ) etAS: 03-593-26 P2E: 121167 | J41/J42 OEC DROP TO BE CONFIRMED by Tuesday | F19 Revisit (DS) + AC Reworks + Cage + RRU installation P2E:143071 | J41/J42 OEC DROP TO BE CONFIRMED by Tuesday |  |  | E15 IBC Revisit | E15 IBC Revisit | E15 IBC Revisit | SB | SB |  |  | E18 Morley Station Revisit | E18 Morley Station Revisit | E18 Morley Station Revisit | E18 Morley Station Revisit | E18 Morley Station Revisit |  |  | R44 IBC | R44 IBC | R44 IBC | R44 IBC | R44 IBC |  |  | R44 IBC | R44 IBC
Anoop | Job Name | Public Holiday | R21 Revisit MOA (PO1 - James Macneall - 0427 816 906 ) etAS: 03-593-26 P2E: 121167 | R21 Revisit (PO1 - James Macneall - 0427 816 906 ) etAS: 03-593-26 P2E: 121167 | R20 Revisit (PO1 - James Macneall - 0427 816 906 ) eTAS: 03-596-26 | R05 Macro Revisit (No P2E) |  |  | J41/J42 OEC Works | J41/J42 OEC Works | J41/J42 OEC Works | J41/J42 OEC Works | J41/J42 OEC Works |  |  | J10 Macro + TMP +DP | J10 Macro + TMP +DP | J10 Macro + TMP +DP | J10 Macro + TMP +DP | J05 OEC + TMP +DP |  |  | J05 OEC + TMP +DP | J05 OEC + TMP +DP | R25 IER +PO1 | R25 IER +PO1 | R25 IER +PO1 |  |  | F03 Revisit +PO1 | F03 Revisit +PO1
Chris | Job Name | Public Holiday | R21 Revisit MOA (PO1 - James Macneall - 0427 816 906 ) etAS: 03-593-26 P2E: 121167 | R21 Revisit (PO1 - James Macneall - 0427 816 906 ) etAS: 03-593-26 P2E: 121167 | R20 Revisit (PO1 - James Macneall - 0427 816 906 ) eTAS: 03-596-26 | B20/B05 + Cage + RRU + termination |  |  | SB | SB | SB | Flying to Melb | AL | AL | AL | SB | SB | SB | SB | SB |  |  | SB | SB | SB | SB | SB |  |  | SB | SB
Jay's Team | Job Name | Public Holiday | M01A IBC P2E: 130877 | M01A IBC P2E: 130877 | M01A IBC P2E: 130877 | R20 Revisit (MOA) (PO1 - James Macneall - 0427 816 906 ) eTAS: 03-596-26 |  |  | J23 Re-visit Fibre splicing | J23 Re-visit Fibre splicing | F08 Revisit MOA +PO1 | R06 Macro with MOA | R06 Macro with MOA |  |  | J10 Macro with MOA + TMP +DP | J10 Macro with MOA + TMP +DP | J10 Macro with MOA + TMP +DP | J05 Macro with MOA + TMP +DP | J05 Macro with MOA + TMP +DP |  |  | R01 Outdoor Works +MOA | R01 Outdoor Works +MOA | R19 Outdoor Works MOA +PO1 | R19 Outdoor Works MOA +PO1 | SB |  |  | R25 Outdoor +PO1 | R25 Outdoor +PO1
Rabin | Job Name | Public Holiday | Office/WH | Office/WH | Office/WH | Office/WH |  |  | Office/WH | Office/WH | Office/WH | Office/WH | E05 Revisit |  |  | Office/WH | Office/WH | Office/WH | Office/WH | Office/WH |  |  | Office/WH | Office/WH | Office/WH | Office/WH | Office/WH |  |  | SB | SB