## Sheet1
Employee Name |  | 2026-05-01 | 2026-05-02 | 2026-05-03 | 2026-05-04 | 2026-05-05 | 2026-05-06 | 2026-05-07 | 2026-05-08 | 2026-05-09 | 2026-05-10 | 2026-05-11 | 2026-05-12 | 2026-05-13 | 2026-05-14 | 2026-05-15 | 2026-05-16 | 2026-05-17 | 2026-05-18 | 2026-05-19 | 2026-05-20 | 2026-05-21 | 2026-05-22 | 2026-05-23 | 2026-05-24 | 2026-05-25 | 2026-05-26 | 2026-05-27 | 2026-05-28 | 2026-05-29 | 2026-05-30 | 2026-05-31
|  | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
SasiKumar Goonasegaran | Job Name | R36/R37/R38/R39 PUG Tunnel SB |  | F11/F12 + Prestart at 7am | E07/E08 (RRU + Cage+ Cable Tray) + 3P PO1 | E07/E08 (RRU + Cage+ Cable Tray) + 3P PO1 | WAH & TR | WAH & TR | F05 Revisit |  |  | J47/J48 Ext Night (Sunday 8PM - Monday 4AM SOS) + 2 x Cat 5 | J33 IBC NS + PO1 Rob C (NS) | J33 IBC NS + PO1 Rob C (NS) | SL | SL |  |  | J33 Glendalough Revisit - NS - PO1 | J33 Glendalough Revisit - NS - PO1 | J33 Glendalough Revisit - NS - PO1 | E07/E08 Gnangara Tunnel RRU terminations PO1 | E07/E08 Gnangara Tunnel RRU terminations PO1 |  |  | T08/T09 Glen Iris Tunnel (NS) + Cat 5 (NS) | T08/T09 Glen Iris Tunnel (NS) + Cat 5 (NS) | T08/T09 Glen Iris Tunnel (NS) + Cat 5 (NS) | R36/R38 (NS + Cabling Works) | R36/R38 (NS + Cabling Works)
Michael Petronio | Job Name | R36/R37/R38/R39 PUG Tunnel SB |  | F11/F12 + Prestart at 7am | J18 Revisit + EWP | E09/E10/E11/E12 Stand by (8pm Start) | E09/E10/E11/E12 (Tunnel + RFS Works + (RRU + Cage Install) NS | J28 Alkimos Station IBC - PO1 (NS) | J28 Alkimos Station IBC - PO1 |  |  | J47/J48 Ext Night (Sunday 8PM - Monday 4AM SOS) + 2 x Cat 5 | J47/J48 Roe Street WODZ Cage Works + PO1 Tim A | J47/J48 Roe Street WODZ Cage Works + PO1 Tim A | SL | SL |  |  | J33 Glendalough Revisit - NS - PO1 | J33 Glendalough Revisit - NS - PO1 | J33 Glendalough Revisit - NS - PO1 | E07/E08 Gnangara Tunnel RRU terminations PO1 | E07/E08 Gnangara Tunnel RRU terminations PO1 |  |  | T08/T09 Glen Iris Tunnel (NS) + Cat 5 (NS) | T08/T09 Glen Iris Tunnel (NS) + Cat 5 (NS) | T08/T09 Glen Iris Tunnel (NS) + Cat 5 (NS) | R36/R38 (NS + Cabling Works) | R36/R38 (NS + Cabling Works)
Noman Aslam | Job Name | T13 Snags Closure (DS) |  |  | J29 (2x Scissor Lifts) NS (PO1) | J29 (2x Scissor Lifts) NS (PO1 Ben) | J29 (2x Scissor Lifts) NS (PO1 Ben) | J29 (2x Scissor Lifts) NS (PO1 Ben) | Training |  |  | J29 NS + PO1 TBC | F08 Revisit IER + SPD termination | F08 Revisit IER + SPD termination | F08 Revisit IER + SPD termination | J29 NOI |  |  | J14 OEC Works | J14 OEC Works | J14 OEC Works + Splicing Works | E01/J24 Rest Day | E01/J24 |  |  | J39/J40 SPD Rework | J39/J40 SPD Rework | SB | SB | SB |  |  | M01A IBC
Naveen Suragani | Job Name | R36/R37/R38/R39 PUG Tunnel SB |  | F11/F12 + Prestart at 7am | J18 Revisit + EWP | E09/E10/E11/E12 Stand by (8pm Start) | E09/E10/E11/E12 (Tunnel + RFS Works + (RRU + Cage Install) NS | F05 Revisit | F05 Revisit |  |  | R23 Revisit indoor | R07 OEC + Splicing | R07 OEC | J19 Internal + PO1 Mark H | J19 Internal + PO1 Mark H + Splicing Works |  |  | J24 Revisit + PO1 | J24 Revisit + PO1 | J21 Revisit | J21 Revisit | J21 Revisit |  |  | T08/T09 Glen Iris Tunnel (NS) + Cat 5 (NS) | T08/T09 Glen Iris Tunnel (NS) + Cat 5 (NS) | T08/T09 Glen Iris Tunnel (NS) + Cat 5 (NS) | SB | SB
Birren | Job Name | E05 Revisit (PO1 3rd Party) |  |  | J29 (2x Scissor Lifts) NS (PO1) | J28 Alkimos Station IBC - PO1 | J28 Alkimos Station IBC - PO1 | J28 Alkimos Station IBC - PO1 | J28 Alkimos Station IBC - PO1 |  |  | J28 Yenchep IBC + PO1 Jeremy M - NS | J28 Yenchep IBC + PO1 Jeremy M - NS | J28 Yenchep IBC + PO1 Jeremy M - NS | J28 Yenchep IBC + PO1 Jeremy M - NS | J28 Yenchep IBC + PO1 Jeremy M - NS |  |  | J24 Revisit + PO1 | J24 Revisit + PO1 | J21 Revisit | J21 Revisit | J21 Revisit |  |  | E15 Revisit + Cladding (PO1) IBC | E15 Revisit + Cladding (PO1) IBC | E15 Revisit + Cladding (PO1) IBC | E15 Revisit + Cladding (PO1) IBC | E15 Revisit + Cladding (PO1) IBC
Aqeel Hussain | Job Name | E05 Revisit (PO1 3rd Party) |  | M09/M10 Prestart at 7am | Training | R09 IER works | J18 Revisit | J18 Revisit | R07 OEC |  |  | R07 OEC | R07 OEC + Splicing | R07 OEC | R05 Revisit + Splicing Works | SL | M19 PTOCC SS Only |  | J32 Revisit (Ben M) | J32 Revisit (Ben M) | J32 Revisit (Ben M) | J32 Revisit (Ben M) | J32 Revisit (Ben M) |  |  | J32 Revisit (Ben M) | J32 Revisit (Ben M) | J32 Revisit (Ben M) | J32 Revisit (Ben M) | J32 Revisit (Ben M)
Garry | Job Name | F19 NS (Tues 7pm - 5am) + TMP |  |  | F19 NS (Tues 7pm - 5am) + TMP | J28 Alkimos Station IBC NS - PO1 | J30 Alkimos Station IBC + PO1 Ben M | J28 Alkimos Station IBC - PO1 (NS) | J30 Alkimos Station IBC + PO1 Ben M |  |  | J30 Alkimos IBC + PO1 Ben M - NS | J30 Alkimos IBC + PO1 Ben M - NS | J30 Alkimos IBC + PO1 Ben M - NS | J30 Alkimos IBC + PO1 Ben M - NS | J30 Alkimos IBC + PO1 Ben M - NS |  |  | J32 Revisit (Ben M) | J32 Revisit (Ben M) | J32 Revisit (Ben M) | J32 Revisit (Ben M) | J32 Revisit (Ben M) |  |  | J32 Revisit (Ben M) | J32 Revisit (Ben M) | J32 Revisit (Ben M) | J32 Revisit (Ben M) | J32 Revisit (Ben M)
Desire Chitsiga | Job Name | J28 Yanchep IBC NS + SL + PO1 (Ben Mogg) |  |  | J28 Alkimos Station IBC - PO1 | E09/E10/E11/E12 Stand by (8pm Start) | E09/E10/E11/E12 (Tunnel + RFS Works + (RRU + Cage Install) NS | J28 Alkimos Station IBC - PO1 (NS) | J28 Alkimos Station IBC - PO1 |  |  | J28 Yenchep IBC + PO1 Jeremy M - NS | J28 Yenchep IBC + PO1 Jeremy M - NS | J28 Yenchep IBC + PO1 Jeremy M - NS | J28 Yenchep IBC + PO1 Jeremy M - NS | J28 Yenchep IBC + PO1 Jeremy M - NS |  |  | J32 Revisit (Ben M) | J32 Revisit (Ben M) | J32 Revisit (Ben M) | J32 Revisit (Ben M) | J32 Revisit (Ben M) |  |  | J32 Revisit (Ben M) | J32 Revisit (Ben M) | J32 Revisit (Ben M) | J32 Revisit (Ben M) | J32 Revisit (Ben M)
Panji | Job Name | T13 Snags Closure (DS) |  |  | J30 Alkimos Station IBC + PO1 Ben M | J28 Alkimos Station IBC NS - PO1 | J30 Alkimos Station IBC + PO1 Ben M | J29 (2x Scissor Lifts) NS (PO1 Ben) | J30 Alkimos Station IBC + PO1 Ben M |  |  | J30 Alkimos IBC + PO1 Ben M - NS | J30 Alkimos IBC + PO1 Ben M - NS | J30 Alkimos IBC + PO1 Ben M - NS | J30 Alkimos IBC + PO1 Ben M - NS | J30 Alkimos IBC + PO1 Ben M - NS |  |  | J32 Revisit (Ben M) | J32 Revisit (Ben M) | J32 Revisit (Ben M) | J32 Revisit (Ben M) | J32 Revisit (Ben M) |  |  | J32 Revisit (Ben M) | J32 Revisit (Ben M) | J32 Revisit (Ben M) | J32 Revisit (Ben M) | J32 Revisit (Ben M)
Sebin Sebastian | Job Name | F19 NS (Tues 7pm - 5am) + TMP |  |  | F19 NS (Tues 7pm - 5am) + TMP | F19 NS (Tues 7pm - 5am) | J30 Alkimos Station IBC + PO1 Ben M | F19 NS (Tues 7pm - 5am) | J30 Alkimos Station IBC + PO1 Ben M |  |  | J30 Alkimos IBC + PO1 Ben M - NS | J30 Alkimos IBC + PO1 Ben M - NS | J30 Alkimos IBC + PO1 Ben M - NS | J30 Alkimos IBC + PO1 Ben M - NS | J30 Alkimos IBC + PO1 Ben M - NS |  |  | J30 Alkimos IBC + PO1 - NS | J30 Alkimos IBC + PO1 - NS | E18 Revisit + Cladding (PO1) IBC | E18 Revisit + Cladding (PO1) IBC | E18 Revisit + Cladding (PO1) IBC |  |  | E18 Revisit + Cladding (PO1) IBC | E18 Revisit + Cladding (PO1) IBC | E18 Revisit + Cladding (PO1) IBC | E18 Revisit + Cladding (PO1) IBC | E18 Revisit + Cladding (PO1) IBC
Chima | Job Name | R36/R37/R38/R39 PUG Tunnel (No EWP Requirement) (Ext Night) (2 - 3 Persons Cat 5) (Tunnel Ladders) |  |  | J29 (2x Scissor Lifts) NS (PO1) | J29 (2x Scissor Lifts) NS (PO1) | J29 (2x Scissor Lifts) NS (PO1) | J29 (2x Scissor Lifts) NS (PO1) | F05 Revisit |  |  | J29 NS + PO1 TBC | F08 Revisit IER + SPD termination | F08 Revisit IER + SPD termination | J47/J48 Roe Street WODZ Cage Works + PO1 Tim A | J47/J48 Roe Street WODZ Cage Works + PO1 Peter MC |  |  | J30 Alkimos IBC + PO1 - NS | J30 Alkimos IBC + PO1 - NS | E18 Revisit + Cladding (PO1) IBC | E18 Revisit + Cladding (PO1) IBC | E18 Revisit + Cladding (PO1) IBC |  |  | E18 Revisit + Cladding (PO1) IBC | E18 Revisit + Cladding (PO1) IBC | E18 Revisit + Cladding (PO1) IBC | E18 Revisit + Cladding (PO1) IBC | E18 Revisit + Cladding (PO1) IBC
Cosmas Dzvifu | Job Name | F19 NS (Tues 7pm - 5am) + TMP |  |  | F19 NS (Tues 7pm - 5am) + TMP | F19 NS (Tues 7pm - 5am) | J30 Alkimos Station IBC + PO1 Ben M | F19 NS (Tues 7pm - 5am) | J30 Alkimos Station IBC + PO1 Ben M |  |  | J30 Alkimos IBC + PO1 Ben M - NS | J30 Alkimos IBC + PO1 Ben M - NS | J30 Alkimos IBC + PO1 Ben M - NS | J30 Alkimos IBC + PO1 Ben M - NS | J30 Alkimos IBC + PO1 Ben M - NS |  |  | J30 Alkimos IBC + PO1 - NS | J30 Alkimos IBC + PO1 - NS | E18 Revisit + Cladding (PO1) IBC | E18 Revisit + Cladding (PO1) IBC | E18 Revisit + Cladding (PO1) IBC |  |  | E18 Revisit + Cladding (PO1) IBC | E18 Revisit + Cladding (PO1) IBC | E18 Revisit + Cladding (PO1) IBC | E18 Revisit + Cladding (PO1) IBC | E18 Revisit + Cladding (PO1) IBC
Siya | Job Name | J28 Yanchep IBC NS + SL + PO1 (Ben Mogg) |  |  | E07/E08 (RRU + Cage+ Cable Tray) + 3P PO1 | R09 IER works | J18 Revisit | J18 Revisit | R07 OEC |  |  | J28 Yenchep IBC + PO1 Jeremy M - NS | J28 Yenchep IBC + PO1 Jeremy M - NS | J33 IBC NS + PO1 Rob C (NS) | J28 Yenchep IBC + PO1 Jeremy M - NS | J28 Yenchep IBC + PO1 Jeremy M - NS |  |  | J30 Alkimos IBC + PO1 - NS | J30 Alkimos IBC + PO1 - NS | E18 Revisit + Cladding (PO1) IBC | E18 Revisit + Cladding (PO1) IBC | E18 Revisit + Cladding (PO1) IBC |  |  | E18 Revisit + Cladding (PO1) IBC | E18 Revisit + Cladding (PO1) IBC | E18 Revisit + Cladding (PO1) IBC |  | E18 Revisit + Cladding (PO1) IBC
Sreerag Varikkottil | Job Name | R36/R37/R38/R39 PUG Tunnel (No EWP Requirement) (Ext Night) (2 - 3 Persons Cat 5) (Tunnel Ladders) |  | M09/M10 Prestart at 7am | Training | R09 IER works | WAH & TR | WAH & TR | F05 Revisit |  |  | J30 Alkimos IBC + PO1 Ben M - NS | J47/J48 Roe Street WODZ Cage Works + PO1 Tim A | J47/J48 Roe Street WODZ Cage Works + PO1 Tim A | J47/J48 Roe Street WODZ Cage Works + PO1 Tim A | TBC |  |  | J28 Yenchep IBC + PO1 | J28 Yenchep IBC + PO1 | E15 Revisit + Cladding (PO1) IBC | E15 Revisit + Cladding (PO1) IBC | E15 Revisit + Cladding (PO1) IBC |  |  | E15 Revisit + Cladding (PO1) IBC | E15 Revisit + Cladding (PO1) IBC | E15 Revisit + Cladding (PO1) IBC | E15 Revisit + Cladding (PO1) IBC | E15 Revisit + Cladding (PO1) IBC
Mudassar Ayaz | Job Name | R28 Anketell Tunnel (PO1 Chris) Closure + HOP |  | M09/M10 Prestart at 7am | Training | E09/E10/E11/E12 Stand by (8pm Start) | E09/E10/E11/E12 (Tunnel + RFS Works + (RRU + Cage Install) NS | Roe Street CW Supervision + E02/E03 | J29 PIM Clearance |  |  | R23 Revisit indoor | R23 Revisit indoor | T08/T09 Glen Iris Tunnel Prep works (11pm Prestart) | T08/T09 Glen Iris Tunnel NS | T08/T09 Glen Iris Tunnel NS |  |  | J28 Yenchep IBC + PO1 | J28 Yenchep IBC + PO1 | E15 Revisit + Cladding (PO1) IBC | E15 Revisit + Cladding (PO1) IBC | E15 Revisit + Cladding (PO1) IBC |  |  | T08/T09 Glen Iris Tunnel (NS) + Cat 5 (NS) | T08/T09 Glen Iris Tunnel (NS) + Cat 5 (NS) | T08/T09 Glen Iris Tunnel (NS) + Cat 5 (NS) | SB | E09/E10 OEC Splicing
Barita Sitompul | Job Name | J28 Yanchep IBC NS + SL + PO1 (Ben Mogg) |  |  | J29 (2x Scissor Lifts) NS (PO1) | J28 Alkimos Station IBC - PO1 | J28 Alkimos Station IBC - PO1 | J28 Alkimos Station IBC - PO1 (NS) | J28 Alkimos Station IBC - PO1 |  |  | R23 Revisit indoor | R23 Revisit indoor | R23 Revisit indoor | J19 Internal + PO1 Mark H | J19 Internal + PO1 Mark H |  |  | J28 Yenchep IBC + PO1 | J28 Yenchep IBC + PO1 | E15 Revisit + Cladding (PO1) IBC | E15 Revisit + Cladding (PO1) IBC | E15 Revisit + Cladding (PO1) IBC |  |  | E15 Revisit + Cladding (PO1) IBC | E15 Revisit + Cladding (PO1) IBC | E15 Revisit + Cladding (PO1) IBC | E15 Revisit + Cladding (PO1) IBC | E15 Revisit + Cladding (PO1) IBC
Kaka | Job Name | J28 Yanchep IBC NS + SL + PO1 (Ben Mogg) |  |  | J28 Alkimos Station IBC - PO1 | J28 Alkimos Station IBC - PO1 | J28 Alkimos Station IBC - PO1 | J28 Alkimos Station IBC - PO1 (NS) | J28 Alkimos Station IBC - PO1 |  |  | J28 Yenchep IBC + PO1 Jeremy M - NS | J28 Yenchep IBC + PO1 Jeremy M - NS | J28 Yenchep IBC + PO1 Jeremy M - NS | J28 Yenchep IBC + PO1 Jeremy M - NS | J28 Yenchep IBC + PO1 Jeremy M - NS |  |  | J28 Yenchep IBC + PO1 | J28 Yenchep IBC + PO1 | E15 Revisit + Cladding (PO1) IBC | E15 Revisit + Cladding (PO1) IBC | E15 Revisit + Cladding (PO1) IBC |  |  | E15 Revisit + Cladding (PO1) IBC | E15 Revisit + Cladding (PO1) IBC | E15 Revisit + Cladding (PO1) IBC | E15 Revisit + Cladding (PO1) IBC | E15 Revisit + Cladding (PO1) IBC
Sudeep | Job Name | F19 NS (Tues 7pm - 5am) + TMP |  |  | E09/E10 IER + OEC + P01 | E09/E10 IER + OEC + P01 | E09/E10 IER + OEC + P01 | E09/E10 IER + OEC + P01 | E09/E10 IER + OEC + P01 |  |  | R09 IER + Fibre Testing (DS) | R09 IER + SPD Termination (DS) | R09 IER + SPD Termination (DS) | R09 IER + SPD Termination (DS) | T08/T09 Glen Iris Tunnel - WODZ - Rack Installation + P01 |  |  | T08/T09 Comms Room (PO1) + Peter M | T08/T09 Comms Room (PO1) + Peter M | T08/T09 Comms Room (PO1) + Peter M | T08/T09 Comms Room (PO1) + Peter M | T08/T09 Comms Room (PO1) + Peter M |  |  | J39/J40 SPD Rework | J39/J40 SPD Rework | SB | SB | SB
Anoop | Job Name | R36/R37/R38/R39 PUG Tunnel (No EWP Requirement) (Ext Night) (2 - 3 Persons Cat 5) (Tunnel Ladders) |  | F11/F12 + Prestart at 7am | E09/E10 IER + OEC + P01 | E09/E10 IER + OEC + P01 | E09/E10 IER + OEC + P01 | E09/E10 IER + OEC + P01 | E09/E10 IER + OEC + P01 |  |  | R09 IER + Fibre Testing (DS) | R09 IER + SPD Termination (DS) | R09 IER + SPD Termination (DS) | R09 IER + SPD Termination (DS) | T08/T09 Glen Iris Tunnel - WODZ - Rack Installation + PO1 |  |  | T08/T09 Comms Room (PO1) + Peter M | T08/T09 Comms Room (PO1) + Peter M | T08/T09 Comms Room (PO1) + Peter M | T08/T09 Comms Room (PO1) + Peter M | T08/T09 Comms Room (PO1) + Peter M |  |  | M01A IBC | M01A IBC | M01A IBC | M01A IBC | M01A IBC
Jimmy | Job Name | R36/R37/R38/R39 PUG Tunnel SB |  |  | E07/E08 (RRU + Cage+ Cable Tray) + 3P PO1 | E07/E08 (RRU + Cage+ Cable Tray) + 3P PO1 | Standby + DT Claimed from Nokia | Mockup RRUs + Cage | Standby |  |  | J28 Yenchep IBC + PO1 Jeremy M - NS | J33 IBC NS + PO1 Rob C (NS) | J33 IBC NS + PO1 Rob C (NS) | T08/T09 Glen Iris Tunnel NS | J28/J30 AC Connection |  |  | R37/R39 IER + RRU Installation + Termination (DS) | R37/R39 IER + RRU Installation + Termination (DS) | R37/R39 IER + RRU Installation + Termination (DS) | T08/T09 Comms Room (PO1) (RRU Installation + Cage Installation) | T08/T09 Comms Room (PO1) (RRU Installation + Cage Installation) | AL | AL | AL | AL | AL | AL | AL | AL | AL
Chris |  | 2026-05-14: SW Training; 2026-05-15: WH Clea up; 2026-05-18: R37/R39 IER + RRU Installation + Termination (DS); 2026-05-19: R37/R39 IER + RRU Installation + Termination (DS); 2026-05-20: R37/R39 IER + RRU Installation + Termination (DS); 2026-05-21: T08/T09 Comms Room (PO1) (RRU Installation + Cage Installation); 2026-05-22: T08/T09 Comms Room (PO1) (RRU Installation + Cage Installation); 2026-05-25: M01A IBC; 2026-05-26: M01A IBC; 2026-05-27: M01A IBC; 2026-05-28: M01A IBC; 2026-05-29: M01A IBC
Reymar | Job Name | R09 CW |  |  | E07/E08 OEC + P01 | E07/E08 OEC + P01 | E07/E08 OEC + P01 | E07/E08 OEC + P01 | E07/E08 OEC + P01 |  |  | J47/J48 / J60 Roe Street WODZ OEC + PO1 Tim A | J47/J48 / J60 Roe Street WODZ OEC + PO1 Tim A | J47/J48 / J60 Roe Street WODZ OEC + PO1 Tim A | J47/J48 / J60 Roe Street WODZ OEC + PO1 Angus R | J47/J48 Roe Street WODZ Cage Works + PO1 Peter MC |  |  | R37/R39 IER + Cabling RRU | R37/R39 IER + Cabling RRU | R37/R39 IER + Cabling RRU | R37/R39 IER + Cabling RRU | R37/R39 IER + Cabling RRU |  |  | J60/J47/J48 Remaining Works | E07/E08 SPD + IER Works | E07/E08 SPD + IER Works | SB | SB
Rabin | Job Name | R28 Anketell Tunnel (PO1 Chris) Closure + HOP |  |  | E07/E08 OEC + P01 | E07/E08 OEC + P01 | E07/E08 OEC + P01 | E07/E08 OEC + P01 | E07/E08 OEC + P01 |  |  | J47/J48/J60 Roe Street WODZ OEC + PO1 Tim A | J47/J48/J60 Roe Street WODZ OEC + PO1 Tim A | J47/J48 / J60 Roe Street WODZ OEC + PO1 Novo | J47/J48 / J60 Roe Street WODZ OEC + PO1 Angus R | J47/J48 Roe Street WODZ Cage Works + PO1 Peter MC |  |  | R37/R39 IER + Cabling RRU | R37/R39 IER + Cabling RRU | R37/R39 IER + Cabling RRU | R37/R39 IER + Cabling RRU | R37/R39 IER + Cabling RRU |  |  | J60/J47/J48 Remaining Works | E07/E08 SPD + IER Works | E07/E08 SPD + IER Works | SB | SB
Jay's Team | Job Name | E05 Revisit (PO1 Novocon) |  |  | J47/J48/J60 OEC Delivery - PO1 Peter M | F05 Revisit Outdoor works | R09 Outdoor works + TMP | R09 Outdoor works + TMP | R05 Revisit (TMP) |  |  | F08 Revisit 2 people only Outdoor works + SPD | J23 Revisit 2 people only Outdoor + EWP | R23 Revisit 2 people only Outdoor | J19 Revisit 2 people only Outdoor + EWP + PO1 Mark H | No work |  |  | J60 + EWP + PO1 + Splicing + PO1 (RIW Operator) | J60 + EWP + PO1 + Splicing + PO1 (RIW Operator) | J21 Revisit + Splicing | J14 Revisit Outdoor Works (MOA) | J19 Revisit + Splicing + PO1 |  |  | M01A IBC | M01A IBC | M01A IBC | M01A IBC | M01A IBC